## Features & Deliverables
Feature/Deliverable | Description
Website UI/UX Design | Design of user interface and experience for the web application.
Database Schema | Structured database schema for efficient data management.
API Endpoints | RESTful API endpoints for backend communication.
Frontend Application | Interactive frontend application for user engagement.
QA Test Plan | Comprehensive test plan for quality assurance.
Deployment Strategy | Plan for deploying the web application to production.
The website for Cravo (https://www.cravo.com/en) showcases a variety of features focused on presenting their products, technologies, and expertise in agricultural solutions. Here's a detailed list of web app features based on the structure and content available on their site:
1. Home Page
- Carousel slider with images highlighting Cravo's retractable roof solutions.
- Quick introduction section about Cravo's approach to agriculture.
- Featured products and technologies section.
- Latest news and updates snippet.
- Testimonials from customers.
- Call-to-action (CTA) buttons for contacting Cravo and learning more about their solutions.
2. Product and Solutions Overview
- Detailed descriptions of different retractable roof models and their applications.
- Sections dedicated to specific crops like fruits, vegetables, flowers, and specialty areas like cannabis and nursery operations.
- Benefits of using Cravo's solutions, including climate control and enhanced crop production.
- Interactive elements like videos and image galleries showcasing the technology in action.
3. About Us
- Company history and background.
- Mission, vision, and values.
- Team introduction or leadership section.
- Sustainability and innovation focus.
4. Resources
- Blog or news section with articles on agriculture practices, case studies, and company updates.
- FAQ section addressing common queries about the products and services.
- Downloadable resources such as product brochures, technical guides, and whitepapers.
5. Contact Us
- Contact form for inquiries, feedback, or support requests.
- Contact information including phone numbers, email addresses, and physical address.
- Interactive map showing Cravo's location.
- Links to social media profiles.
6. Technical Support and Services
- Information on installation services, technical support, and maintenance plans.
- Training resources for customers on how to use and maintain the retractable roof systems.
7. Customer Portal (if available)
- Login area for customers to access personalized information, order history, and support resources.
8. Search Functionality
- Site-wide search feature to quickly find information on products, articles, and resources.
9. Language Selection
- Option to switch between different language versions of the site, if available.
10. Newsletter Subscription
- Signup form for receiving updates, news, and insights related to agricultural solutions and Cravo's offerings.
11. Social Media Integration
- Links or widgets for Cravo's social media pages for additional engagement and updates.
12. Responsive Design
- A mobile-friendly website layout that adjusts content and navigation for optimal viewing on various devices.
These features are designed to provide a comprehensive overview of Cravo's offerings, engage with different stakeholders, and facilitate communication and support.

## Timeline and Phases
Phase | Duration (Weeks) | Calendar Days | Start Date | End Date
Requirements Gathering and Analysis | 2 | 13 | 2024-03-01 | 2024-03-14
Database Design | 3 | 20 | 2024-03-15 | 2024-04-04
API Development with FastAPI | 10 | 66 | 2024-04-05 | 2024-06-10
Frontend Development with Flet | 11 | 10 | 2024-04-05 | 2024-06-20
Testing and Quality Assurance | 5 | 29 | 2024-06-11 | 2024-07-10
Deployment and Maintenance | 1 | 7 | 2024-07-11 | 2024-07-18
145
Formulas:
Duration (Weeks) = ROUNDUP(DAYS([End Date],[Start Date]) /7,0)

## Resource Allocation
Task | Assigned To | Hours Allocated | Hours Allocated Local | Per Hour Charges | Estimated Cost
Project Setup | Project Manager | 40 | 60 | 30 | 1800
Database Setup | Database Administrator | 80 | 120 | 20 | 2400
API Development | Backend Developer | 240 | 360 | 20 | 7200
Frontend Setup | Frontend Developer | 200 | 300 | 20 | 6000
QA Testing | QA Engineer | 160 | 240 | 20 | 4800
Production Deployment | DevOps Engineer | 40 | 60 | 30 | 1800
|  |  |  | Total | 24000 | 16800
7200

## Budget Estimate
Expense Category | First Year Cost | Second Year Cost
Software Development Resource | 24000 | 0
Software (Annual Mainentance) | 0 | 4800
Hosting (annual Recurring) | 3000 | 3000
Miscellaneous | 2000 | 2000
Total | 29000 | 9800

## Risk Management
Risk | Probability | Impact | Mitigation Strategies
Scope Creep | Medium | High | Regular scope review meetings and stakeholder alignment.
Technical Challenges | High | Medium | Continuous training and technical research.
Resource Availability | Low | High | Advance resource planning and hiring as needed.

## Milestones
Milestone | Description | Due Date | Status
Project Kickoff | Official start of the project. | 2024-03-01 | Planned
Database Design Complete | Completion of the database schema design. | 2024-04-04 | Planned
API Development Complete | Completion of API endpoints development. | 2024-05-16 | Planned
Frontend Development Complete | Completion of frontend application development. | 2024-06-20 | Planned
Testing Phase Complete | Completion of all testing activities. | 2024-07-18 | Planned
Project Go-Live | Official release and deployment of the project. | 2024-08-01 | Planned

## Communication Plan
Stakeholder Group | Information Needs | Communication Method | Frequency
Project Team | Project updates, Technical guidance | Meetings, Emails, Slack | Weekly
Management | Project progress and issues | Reports, Presentations | Monthly
Clients | Product updates and feedback | Emails, Newsletters | As needed