## Sheet1
Task | Task Description | Status
Sprint 1 Objective:Establish project foundation and start development on the Resident Input module. | Setup and Resident Input Module
Setup Odoo development environment (Installation Odoo Configuration and Database installation)
Define user roles and permissions
Create the custom module for handling complaints with fields for descriptions, severity, and image uploads.
Implement the review and rating system for resolved complaints.
Begin development on QR code generation for various purposes.
QA
UAT
Sprint 2 Objective:Develop the Technician Performance module and integrate | Technician Performance Module:
Create a module to track complaints assigned to technicians.
Implement the feature to record technicians' response times.
Track reoccurrences of the same fault and develop the KPI Matrix for technician performance metrics.
QA
UAT
Down Time and Occurrence Frequency Modules
Sprint 3 Objective:Focus on Downtime-related functionalities and fault occurrence tracking. | Develop the module for tracking downtime-related complaints.
Categorize faults as mechanical or electric and integrate cost tracking.
Create a module to record fault types, frequency, and associated costs.
Start development on the root cause analysis system.
QA
UAT
Sprint 4 Objective: Implement reporting for average expenses and develop the allowance tracking system for employees. | Average Expenses Reporting and Employee Allowances
Utilize Odoo's reporting capabilities to generate reports on maintenance costs.
Implement geolocation tracking for employees and develop the monthly report generation system for allowances.
QA
UAT
Sprint 5 Objective:Finalize the review rating system and develop the customer validation system. | Review Rating and Customer Validation
Complete the star rating system and comments feature for maintenance services.
Develop the validation system for customer complaints, including picture validation and bill voucher validation.
QA
UAT
Sprint 6 Objective:Enhance finance visibility and conclude project development with final testing and adjustments. | Finance Visibility and Project Wrap-Up
Implement the profit and loss statement feature for maintenance operations.
Conduct comprehensive testing of all modules and features.
Make necessary adjustments based on feedback and testing results.
QA
UAT
Sprint 7 Objective:Application deployment and training and fix intial issues | Deployment and Training
Deploy the application to production environment
Train users on the new system
Gather feedback and address any initial issues
QA
UAT
NOTE: This sprint plan is a guideline and may require adjustments based on the project team's velocity, stakeholder feedback, and any unforeseen challenges. Regular communication and flexibility are key to successfully implementing the project within the Agile framework.